## Sheet1
| Design Document | [10 empty] | Code Complete | [6 empty] | Presentation |  |  | Final Report
Task/Date | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17
Establish Timeline (Mason)
Green = Presentables | bar: 2025-11-25 to 2025-11-27
Blue = Backend
Design Document (All) | [23 empty] | Orange = Critical Structure
Purple = Queries | bar: 2025-11-25 to 2025-12-05
Red = Frontend
Research Dataset (Ian)
Develop CLI (Killian)
Create Graph Class (Ian)
Design and Implement Sort #1 (Killian)
Design and Implement Sort #2
Design Module Structure and UML (Mason)
Implement CSV Parser
Implement Bloom Filter
Implement find_movie_by_title
Implement find_movies_by_actor
Implement find_movies_by_year_and_genre
Implement find_top_10_movies (Mason)
Implement suggest_similar_movies
Implement find_shortest_connection
Queue (Mason)
Heap
Timer
Connect Class Structure
Final Report
Write Presentation
Rehearse Presentation
Heap (Mason)